## Sheet1
Task | Start Date | Duration | End Date
Setting up file sharing | 2016-10-04 | 7 | 2016-10-11
Meeting with client | 2016-10-04 | 7 | 2016-10-11
Meeting with TA | 2016-10-12 | 7 | 2016-10-19
Coming up with problem statement | 2016-10-11 | 3 | 2016-10-14
Requirements documents | 2016-10-20 | 15 | 2016-11-04
Decide Graphical icon package | 2016-10-20 | 21 | 2016-11-10
get client confirmation on graphic package | 2016-10-25 | 36 | 2016-11-30
Create the graphics package | 2016-11-01 | 38 | 2016-12-09
Finalize the tools and software needed for the project | 2016-11-01 | 38 | 2016-12-09
implementation of the window | 2017-01-09 | 37 | 2017-02-15
Implementation of the Block Menu | 2017-01-09 | 37 | 2017-02-15
implementation of channels, probe and Skeleton for Blocks | 2017-01-09 | 37 | 2017-02-15
implementation of Input/Output | 2017-02-01 | 42 | 2017-03-15
implementation of variables, constants and Methods | 2017-02-01 | 42 | 2017-03-15
implementation of classes and layers | 2017-02-01 | 42 | 2017-03-15
First User Test | 2017-03-15 | 5 | 2017-03-20
Debugging process | 2017-03-15 | 9 | 2017-03-24
Second User Test | 2017-04-03 | 7 | 2017-04-10
Debugging Process | 2017-04-03 | 12 | 2017-04-15
Third User Test | 2017-04-15 | 5 | 2017-04-20
Debugging Process | 2017-04-15 | 15 | 2017-04-30
Fourth User Test | 2017-05-01 | 9 | 2017-05-10
Debugging Process | 2017-05-01 | 14 | 2017-05-15
Alpha release | 2017-05-20 | 1 | 2017-05-20